## Slide 1: Team Status Report
Team Argus - 04/03/2015

## Slide 2: Project Plan
Tracking through Test Plan and second set of tasks set of development tasks
Cost Analysis
  Planned Cost = 540 hours total (450 up to this point)
  Actual Cost = 425 hours
  Earned Value = 420 hours
  CPI = .988 (Change from 1.03)
  SPI = .933 (Change from .98)

## Slide 3: Application (PixelSense-SDK Layer)
Can read IR LEDs on table.
Working on converting them to strings.
Made it working on specific part of screen.

## Slide 4: Lynx Case 3D Printing
3 Separate Components:
  Lynx Device
  Tablet Case
  Power Bank Case

## Slide 5: Hardware Builds
LED Array through MAX7219
  4x4 array in a 2x8 configuration
  Even power distribution
  Lower power consumption

## Slide 6: Hardware Builds
Phototransistors
  Digital vs. Analog readings
  Reading rate - 10 reads per second
  What’s next

## Slide 7: Android Software
Project Repairs
  Device Filter disappeared
  Library linking broken
  App was erroring out but didn’t give a legible reason
  Buffer overflow

## Slide 8: Android Software
What is working
  Serial input/output
  External modules are now
properly added
  Basic app functionality is
working.

## Slide 9: Android Software
What is next
  Syncing with the table/Lynx
  Error checking/correction
  Attempt to send more complex
data

## Slide 10: SDK Specifications
Preliminary research has been done to tackle the major features of the SDK
Authentication
Orientation
Data Transfer Metadata
Error Detection

## Slide 11: SDK Specifications
Authentication and Orientation
Explored using the LEDs of the Lynx as a unique way to signal its presence without addition features, may use something simpler
Orientation with 3 specific LEDs
Signal with Unique ID parameter (serial number)

## Slide 12: SDK Specifications
Error Detection
Researched into effective error detection techniques for data transfer
Modelling after TCP checksum

## Slide 13: SDK Specification
Transfer MetaData - Preliminary data header
|------------------------16 bits------------------------|
Identification number
Sequence Number
Acknowledgement
type | Flags | checksum
length

## Slide 14: Risk Assessment
Risk | Severity | Probability | Setback | Containment
Hardware failures -Teensy -Nexus 7 -PixelSense -IR LEDs -Phototransistors | Very High | 35% | 1-4 weeks | Use hardware available to test and order new hardware for final product
Android Studio hates us | Moderate | 40% | 3-7 days | Use Eclipse to develop Android application
Shamikul’s addiction to greasy food | Moderate | 134% | 1-2 hours | Utilize wet naps Force Shamikul to wear gloves
Blackjack game on PixelSense table not working | High | 70% | 1 week | Develop a new blackjack application using game engine

## Slide 15: Questions?
Fun Fact #261
Zedd, Jonny, and Shamikul have formed a Hip Hop Dance crew called GNB.
They are terrible.
Notes: :D