## Slide 1: Team Status Report
Team Argus - 05/01/2015

## Slide 2: Project Plan
Tracking through the end of the project
Cost Analysis
  Planned Cost = 925 hours total (650 up to this point)
  Actual Cost = 638 hours
  Earned Value = 590 hours
  CPI = .924 (Change from .988)
  SPI = .907 (Change from .933)

## Slide 3: TagVisualizer with Transfer Layer
Send Stuff from PixelSense
  Converted code from XNA(Game Engine) to WPF(Windows Form).
  Can Flash Binary Characters now.
Tag Visualizer
  First Step of Lynx Authentication
  Can Flash relative to Visualized Tag.

## Slide 4: Android Software
Complete in the sense anything can be sent
Still need to finalize what exactly are we sending

## Slide 5: Android Software
Next
  Game animations need to be optimized
  Splash screen must be completed
  Make it look more aesthetically nice (ie: image buttons, designer box and if time permits OpenGL graphics)

## Slide 6: Hardware
Complete and functional
Possible bugs:
  Pins malfunctioning
  Battery pack is auto shutting off, so a load is required
  Bad components

## Slide 7: Reading Light
Configuring to the new hardware
  Compensating for phototransistors being too close
Making adjustments for new WPF flashes
Future Tasks - Improve accuracy of light reading, implement handshake method of reading to properly sync reading and improve speeds

## Slide 8: Transfer Layer Progress
Significant Setback - “New” Handshake bits
Tag Visualizer - SDK Treasure Hunt / XAML crash course
Future Tasks - Finalize Tag interface / begin work integrating with Lynx Transfer System

## Slide 9: Blackjack Software
Developing in WPF instead of XNA
Transferring logic from old XNA to WPF
Currently:
  Play game in console
Future:
  integrate with GUI we have for Tag Visualizer

## Slide 10: Risk Assessment
Risk | Severity | Probability | Setback | Containment
Hardware failures -Teensy -Nexus 7 -PixelSense -IR LEDs -Phototransistors | Very High | 35% | 1-4 weeks | Use hardware available to test and order new hardware for final product
Trouble integrating Blackjack software(XNA) with and TagVisualizer(WPF) | High | 70% | 1 week | Develop a new blackjack application using WPF (in progress)
Distractions in SD Lab | Moderate | 105% | 30 minutes | Headphones and loud music

## Slide 11: Questions?
Fun Fact #88:
Vishal recently donated his “beard” to science...
...unfortunately they needed an actual beard
Notes: :D