## Slide 1: Team Status Report
Team Argus - 11/14/2014

## Slide 2: SRD Feedback
Peer Review Team : Shoe Per Stars
  Customer Requirements
    less specifications
    wording issues
  Other Requirements
    Cost analysis were not justified
    formatting errors
  Acceptance Criteria
    needs to be more specific
  Need to Add Requirements for SDK

## Slide 3: SDK Requirements (Android & PixelSense)
Both SDKs shall allow customizable light sequences.
Both SDKs shall allow send & receive data both ways, i.e Pixelsense & Lynx.
Both SDKs shall allow expansion of Array of Transmitters.
Both SDKs shall notify their respective devices if Lynx is placed on Pixelsense Table.
Pixelsense SDK shall support multiple Lynx devices.

## Slide 4: Research Results
Hardware
  Headless Arduino Micro
    20 I/O
    32KB Flash
    16MHz Clock Speed
    48mm x 18mm
  Photodiodes vs Regular LED

## Slide 5: Research Results
Software
  USB Host Support
    Android 3.2+
    Compatible Hardware
    USB-A or OTG compatible
tablet
    OTG Devices can be host
or slave
  Protocols for data transfer

## Slide 6: Project Plan
Estimations through Architecture Design
Cost Analysis
  Planned Cost = 337 hours
  Actual Cost = 216 hours
  Earned Value = 246 hours
  CPI = 1.14
  SPI = .73

## Slide 7: Project Plan
Cost Analysis - Since last TSR (10/7)
  Planned Cost = 230 hours added
  Actual Cost = 141 hours completed
  Earned Value = 176 hours earned

## Slide 8: Risk Assessment
Risk | Probability | Setback (weeks) | Severity
Lack of Experience: PixelSense SDK | 100% | 2 | 2
Integration issues | 50% | 4 | 2
Lack of Experience: Game | 80% | 2 | 1.6
Overestimate abilities/under plan | 30% | 4 | 1.2
Change in Requirements | 35% | 4 | 1.4

## Slide 9: Risk Assessment
Risk Containment
Change in Requirements/SRD
  Add SDK requirements
  Less casino game requirements
  Update SRD
  Verify changes with sponsor (Dr. Zaruba)

## Slide 10: What Is Next
Fine Tune Requirements
Confirm SRD with Sponsor (SDK changes)
Submit Final SRD to supervisor next week
Work on Architecture Design
Further Research (Architecture Related)